## COM
Module | Takt | Dates | STEP Job | Script Name | Analyzer | Issue | Incident Raised/ Action taken | Status | Responsible | Category | Spillover Takt | Initial Takts
DDE | T2026.03 | 2026-01-07 | DDE_REGRESSION | CID_2034_DDI_DDE_CHANGE_DOC_TO_DISPLAY_CHANGE_LOG | Divya | UI Change Issue | https://jira.tools.sap/browse/CLMAMCLD-1241- Development backlog open | Passed | SPC Application team | UI Change Issue | T2025.51 | T2025.51
DIS | T2026.03 | 2026-01-07 | DIS_REGRESSION | CID_2041_DDI_DIS_CHANGE_DOC_TO_CHANGE_LOG | Divya | UI Change Issue | https://jira.tools.sap/browse/CLMAMCLD-1241- Development backlog open | Passed | SPC Application team | UI Change Issue | T2025.51 | T2025.51
DDV | T2026.03 | 2026-01-07 | DDV_REGRESSION | Three scripts | Divya | Script maintenance Issue | Script Fix and Rerun required | Passed | Test Automation team | Script maintenance Issue |  | T2026.03
DDV | T2026.03 | 2026-01-13 | DDV_REGRESSION | CID_1377_DDI_DDV_VALIDATATION_CHECK_WHILE_CREATING_AN_OBJECT_WITH_INVALID_DATA | Divya | Application Bug- selector not found/disabled | Script fix to update the locator | Passed | Test Automation team | Application Bug- selector not found/disabled |  | T2026.03
DDV | T2026.09 | 2026-01-28 | DDV_INTEGRATION | CID_1955_DDI_DDV_VALIDATE_REFRESH_REMOTE_SOURCE | Divya | Script maintenance Issue | Wrong data was selected while validation | Passed | Test Automation team | Script maintenance Issue | T2026.07, T2026.09 | T2026.09
DIS | T2026.09 | 2026-01-28 | DIS_REGRESSION | CID_2041_DDI_DIS_CHANGE_DOC_TO_CHANGE_LOG | Divya | Application Bug- selector not found/disabled | Dynamic selectors - xpath fix is in progress | Passed | Test Automation team | Script maintenance Issue | T2026.07, T2026.09 | T2026.09
TDE | T2026.13 | 2026-03-24 | COM_ADT_TDE_REGRESSION | COM_ADT_TDE_CREATE_EDIT_OBSOLETE_OPERATIONS | Gunjan | Application Data Issue | "Responsible Queue" data not provide in manual test for selecting while creating Task Definition. | Passed | SPC Application team | Application Data Issue | T2026.13 | T2026.13
PDE | T2025.11 | 2025-03-11 | CID_3359_CLM_AM_COM_ADT_SERVICE_CATALOG_PROCESS_DEFINITION_INTEG_SPC_COM | CID_3359_CLM_AM_COM_ADT_SERVICE_CATALOG_PROCESS_DEFINITION_INTEG_SPC_COM | Divya | Error message displayed in Note | Application Issue | Passed | SPC Application team | UI Change Issue |  | T2025.11
DRE | T2025.11 | 2025-03-11 | COM_DDI_DRE_CREATE_RECEIVER_AND_VALIDATE_THE_CREATED_RECEIVER_UNDER_VERSIONS_APP | COM_DDI_DRE_CREATE_RECEIVER_AND_VALIDATE_THE_CREATED_RECEIVER_UNDER_VERSIONS_APP | Divya | No results displayed in search List - Application UI Issue | DINC0445926 | Open/New | SPC Application team | UI Change Issue |  | T2025.11
DIS | T2025.11 | 2025-03-11 | CID_1483_DDI_DIS_CREATE_DISTRIBUTION_VIA_DISTRIBUTION_APP | CID_1483_DDI_DIS_CREATE_DISTRIBUTION_VIA_DISTRIBUTION_APP | Divya | Not able to fetch Distribution ID | Script Fix | In Progress | Test Automation team | Script maintenance Issue |  | T2025.11
DDV | T2025.11 | 2025-03-12 | CID_1955_DDI_DDV_VALIDATE_REFRESH_REMOTE_SOURCE | CID_1955_DDI_DDV_VALIDATE_REFRESH_REMOTE_SOURCE | Divya | No results displayed in search List - Application UI Issue | DINC0445926 | Open/New | SPC Application team | UI Change Issue |  | T2025.11
TEX | T2025.13 | 2025-03-19 | ART_TEX_REGRESSION | All | Divya | App could not be opened in A2E | DINC0445976 | Passed | SPC Application team | Application Bug |  | T2025.13
TEX | T2025.13 | 2025-03-19 | CID_3391_CLM_AM_COM_PROCESS_DEF_REMOTE_PROCESS_LOG_INTEG_TEST | CID_3391_CLM_AM_COM_PROCESS_DEF_REMOTE_PROCESS_LOG_INTEG_TEST | Gunjan | After clicking on START button application not navigating to A2Q | Script Fix | Passed | Test Automation team | Script maintenance Issue |  | T2025.13
TEX | T2025.13 | 2025-03-26 | COM_ART_TEX_COMPLETE_APPROVE_ADDNOTE_ABORT_SETTOERROR | COM_ART_TEX_COMPLETE_APPROVE_ADDNOTE_ABORT_SETTOERROR | Divya | UIA-A2E: Approve Task Execution not successful | DINC0452566 | Passed | SPC Application team | Application Bug |  | T2025.13
DDE | T2025.13 | 2025-03-26 | CID_1482_DDI_DDE_CREATE_AND_DELETE_LOCAL_DEFINITION | CID_1482_DDI_DDE_CREATE_AND_DELETE_LOCAL_DEFINITION | Divya | No results displayed in A2E - Enhancement done | Script Enhancement - Clear filters before searching the definition ID | Passed | Test Automation team | Script maintenance Issue |  | T2025.13
CLD | T2025.17 | 2025-04-15 | STEP issue for COM_ART_TEX_REGRESSION |  | Gunjan | STEP: Incorrect Success Count is getting displayed for COM_ART_TEX_REGRESSION module. | DINC0472565 | Passed |  | Step Issue
TEX | T2026.07 | 2026-02-10 | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | Gunjan | Application Data Issue | Wrong data getting displayed while validation | Passed | SPC Application team | Application Data Issue | T2026.07 | T2026.07
TEX | T2026.09 | 2026-02-24 | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | Gunjan | Application Data Issue | Wrong data getting displayed while validation | Passed | SPC Application team | Application Data Issue | T2026.09 | T2026.09
TEX | T2026.11 | 2026-03-05 | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | 2 Jobs - CID_3300_CRT_TEX_COMPLETE_APPROVE_TASK_EXECUTION and CID_3301_CRT_TEX_ABORT_ERROR_TASK_EXECUTION | Gunjan | Application Bug- Status mismatch | Incorrect Status is getting displayed | Passed | SPC Application team | Application Bug | T2026.11 | T2026.11
TEX | T2026.11 | 2026-03-05 | 3 Jobs - CID_3367_CRT_TASK_EXECUTION_PARAMETER_VALUE_CHECK CID_3374_CRT_TASK_EXECUTION_PARAMETER_CHANGE_LOG_TEST CID_3394_CLM_AM_COM_CRT_TASK_EXECUTION_STATUS_CHECK | 3 Jobs - CID_3367_CRT_TASK_EXECUTION_PARAMETER_VALUE_CHECK CID_3374_CRT_TASK_EXECUTION_PARAMETER_CHANGE_LOG_TEST CID_3394_CLM_AM_COM_CRT_TASK_EXECUTION_STATUS_CHECK | Gunjan | Application Bug- Status mismatch | Incorrect Status is getting displayed | Passed | SPC Application team | Application Bug | T2026.11 | T2026.11

## SPC
Module | Takt | Dates | STEP Job | Script Name | Analyzer | Issue | Incident Raised/ Action taken | Status | Responsible | Category | Spillover Takt | Initial Takts
PRE | T2026.03 | 2026-01-05 | CLM_AM_SPC_PRV_COMMUNICATION_CONFIG_GLOBAL_ACCNT_CONFIG_NATIVE | CLM_AM_SPC_PRV_COM_CONFIG_GBAC | Yashaswini | UIA-QPE-QPC: Communication configuration ACE473 shows no records under various tabs | DINC0753192 | Passed | SPC Application team | Application Data Issue |  | T2026.03
ICN | T2026.03 | 2025-12-30 | CLM_AM_SPC_NOTIF_DWN_RSN_SHTNT_NATIVE | CLM_AM_SPC_NOTIF_DWN_RSN_SHTNT | Manjula | UIA_QPE:Getting 400 Bad request for Create Event API request | DINC0750839 | Passed | SPC Application team | Application Bug- API response error
IAM | T2026.07 | 2026-01-01 | CLM_AM_SPC_NOTIF_VERIFY_SUPPORT_PCE_FOR_TCE_NATIVE | CLM_AM_SPC_NOTIF_VERIFY_SUPPORT | Manjula | UIA_QPE: "CLM_AM_SPC_NOTIF_VERIFY_SUPPORT_PCE_FOR_TCE_NATIVE" Job is failing only in STEP working fine in local ECA and ECE | DINC0751711 | Passed | Start Team | Step Issue | T2026.05, T2026.07 | T2026.03
IAM | T2026.03 | 2026-01-05 | CLM_AM_SPC_NOTIF_CUSTOMER_VS_BONUS_PLAN_NATIVE | CLM_AM_SPC_NOTIF_CUSTOMER_VS_BONUS_PLAN | Manjula | UIA-QPE : Exclude externally caused -Yes" is not greater than the entry where column "Exclude externally caused -NO" | DINC0752996 | Passed | SPC Application team | Application Data Issue
ITSM | T2026.09 | 2026-01-07 | CLM_AM_SPC_ITSM_Ticket_ChangeClassifServArea_Alert_NATIVE CLM_AM_SPC_ITSM_Ticket_ChangeClassifServArea_ManualIncident_NATIVE CLM_AM_SPC_ITSM_Ticket_ChangeClassifServArea_Problem_NATIVE CLM_AM_SPC_ITSM_Ticket_ChangeClassifServArea_ServiceRequest_NATIVE | All | Divya | UIA-RPE: ITSM_System field in Monitoring page is disabled after clicking on Edit | DINC0754813 | Passed | SPC Application team | Application Bug- selector not found/disabled | T2026.05, T2026.07, T2026.09 | T2026.03
IPS | T2026.03 | 2026-01-07 | CLM_AM_SPC_SNP_MASTER_PLAN_CANCELLATION_SCENARIO_NATIVE | CLM_AM_SNP_MP_CAN_WAV_SKIP_NOT | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-07 | CLM_AM_SPC_SNP_MASTER_PLAN_CHANGE_SCHEDULE_SD_PARAMETERS_NATIVE | CLM_SPC_MSTR_PLN_CN_SCH_PAR_SD | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-07 | CLM_AM_SPC_SNP_MASTER_PLAN_CHANGE_SCHEDULE_SD_PARAMETERS_NATIVE | CLM_AM_MP_CREATE_MASTER_PLAN | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-07 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_SCDE_WITHIN_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WSCDE_WCMP | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-07 | CLM_AM_SPC_SNP_MASTER_PLAN_withoutSCDE_nonCMP_NATIVE | CLM_AM_SPC_SNP_MP_WOSCDE_NOCMP | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_DISABLE_CUST_NOTIFICATION_NATIVE | MASTER_PLAN_DISABLE_CUST_NOT | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WITH_CMP | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_TENANT_NATIVE | CLM_AM_SPC_SNP_MP_TENANT_NEW | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_SER_EXE_INCL_APS_APP_NATIVE | CLM_AM_SPC_SNP_CRT_MSTRP_WAV1 | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MP_UPDT_NOTIF_NATIVE | CLM_AM_SNP_UPDT_NOTIF_MP_WAVE | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_DELAY_STRETCH_PROCESS_START_NATIVE | CLM_MST_PLN_DELY_STRCH_PRO_STR | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_CHK_ONLINE_DEPLOYABLE_NATIVE | CLM_AM_SPC_SNP_MSTR_ONLINE_DEP | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MP_NTIF_EVT_CRT_NATIVE | CLM_AM_SPC_MP_ISL_NTIF_EVT_CRT | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MP_PVNT_DPL_ANC_NATIVE | CLM_AM_SPC_PNE_MP1 | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MP_PVT_DPL_ANC2_NATIVE | CLM_AM_SPC_PNE_MP_W1 | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_WAVE_NOT_CANCELLED_UNTIL_PLANNED_START_TIME_NATIVE | CLM_AM_SPC_WAVE_NOCAN_STILDATE | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MP_RESCHEDULE_DOWNTIME_END_TIME_NATIVE | CLM_AM_SPC_PNE_MP_RSCH_DN_ENT | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MP_SE_START_DISTR_DATA_CENTER_TENANT_DENSITY_NATIVE | CLM_AM_SPC_PNE_MP_SE_SRT_DIS_D | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_ENABLE_CUSTOMER_NOTIFICATION_NATIVE | CLM_SPC_MSTR_PLN_CUST_NOTIF_EN | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_NATIVE | CLM_AM_MSTER_PLN_LNDSCAPE_CONS | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_SNP_MASTER_PLAN_SEND_CONSOLIDATED_ANNOUNCEMENT_NATIVE | CLM_AM_SPC_CRT_MP_CN1 | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-08 | CLM_AM_SPC_IPS_DEFAULT_MP_TEXT_NATIVE | CLM_AM_SPC_IPS_DEFAULT_MP_TEXT | Sushma | Service definition ID field xapth changes. |  | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
ISS | T2026.03 | 2026-01-06 | Many Step jobs are failing in Native and QPC | Many Step jobs are failing in Native and QPC | Hamsa | UIA_QPE/QPC: Clicking of Search button in Ticket ID search field is not working in Monitoring page in STEP execution. | DINC0752977 - START | Passed | Start Team | Step Issue |  | T2026.03
ICSM | T2026.07 | 2026-01-06 | CLM_AM_SPC_ICSM_PERFORMANCE_TEST_CSR_TICKET_CREATION_BY_API_NATIVE | CLM_AM_SPC_ICSM_PERFORMANCE_TEST_CSR_TICKET_CREATION_BY_API_NATIVE | Hamsa | UIA-QPE: API response time is greater than expected response time of 5 seconds | DINC0753159 | Passed | SPC Application team | Application Bug- API response error | T2026.05, T2026.07 | T2026.03
IPS | T2026.03 | 2026-01-09 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_NATIVE | CLM_AM_MSTER_PLN_LNDSCAPE_CONS | Sushma | Updated script as per the enhancement done w.r.t to consistency status and application log. | DINC0740281 | Passed | SPC Application team | UI Enhancement by Dev |  | T2026.03
ISS | T2026.03 | 2026-01-11 | CLM_AM_SPC_ISS_CANCEL_SCHEDULED_SE_HOTFIX_QPC CLM_AM_SPC_SNP_REG_SPECIFIC_NATIVE | CLM_AM_SPC_ISS_CANCEL_SCHEDULED_SE_HOTFIX_QPC CLM_AM_SPC_SNP_REG_SPECIFIC_NATIVE | Hamsa | UIA-QPE: RBAM Error displayed in Service Definition page. | DINC0758827 | Passed | SPC Application team | Application Bug- Save fails |  | T2026.03
ISS | T2026.03 | 2026-01-11 | CLM_AM_SPC_RECURRENCE_DCIS_CREATE_DELETE_NATIVE | CLM_AM_SPC_RECURRENCE_DCIS_CREATE_DELETE_NATIVE | Hamsa | Added steps to filter by name in the script | Added steps to filter by name in the script | Passed | Test Automation team | Script maintenance Issue |  | T2026.03
ISS | T2026.07 | 2026-01-11 | CLM_AM_SPC_SNP_VALIDATION_IN_SERVICE_EXECUTION_WHILE_CHANGING_SDID_IN_SEID_NATIV | CLM_AM_SPC_SNP_VALIDATION_IN_SERVICE_EXECUTION_WHILE_CHANGING_SDID_IN_SEID_NATIV | Hamsa | UIA-QPE: SE is in cancelled status it should be in Scheduled status. | DINC0758782 | Passed | SPC Application team | Application Bug- Status mismatch | T2026.05, T2026.07 | T2026.03
ICN | T2026.13 | 2026-01-13 | CLM_AM_SPC_NOTIF_PLND_MNTNC_SU_NATIVE | CLM_AM_SPC_NOTIF_PLND_MNTNC_SU | Yashaswini | UIA-QPE: Template name doesn't show value help button in send notification for all systems popup in the test workflow | DINC0760138 | Open/New | SPC Application team | Oberon5 UI Issue | T2026.05, T2026.07, T2026.09, T2026.11, T2026.13 | T2026.03
IES | T2026.03 | 2025-12-30 | CLM_AM_SPC_SNP_CALB_RSN_GNRL_TST_NATIVE | CLM_AM_SPC_SNP_CREAT_TICKET_SE | Kavitha | UIA_QPE/QPC: Clicking of Search button in Ticket ID search field is not working in Monitoring page in STEP execution. | DINC0750737 | Passed | Start Team | Start Issue |  | T2026.03
IES | T2026.03 | 2026-01-09 | CLM_AM_SPC_SNP_REPORT_UNCLEAN_WORK_TICKETS_NATIVE | CLM_SPC_SNP_UNCLEN_WRK_TICKETS | Kavitha | Re-recorded the ticket id export step with new xpath |  | Passed | Start Team | Start Issue |  | T2026.03
IPS | T2026.03 | 2025-12-29 | CLM_AM_SPC_SNP_MASTER_PLAN_DELAY_STRETCH_PROCESS_START_NATIVE | CLM_MST_PLN_DELY_STRCH_PRO_STR | Kavitha | Added New button enable validation in script as per manual |  | Passed | Test Automation team | Script maintenance Issue |  | T2026.03
IPS | T2026.03 | 2025-12-29 | CLM_AM_SPC_PNE_MP_NTIF_EVT_CRT_NATIVE | CLM_AM_SPC_MP_ISL_NTIF_EVT_CRT | Kavitha | Added New button enable validation in script as per manual |  | Passed | Test Automation team | Script maintenance Issue |  | T2026.03
IPS | T2026.03 | 2025-12-29 | CLM_AM_SPC_SNP_MASTER_PLAN_ENABLE_CUSTOMER_NOTIFICATION_NATIVE | CLM_SPC_MSTR_PLN_CUST_NOTIF_EN | Kavitha | Added New button enable validation in script as per manual |  | Passed | Test Automation team | Script maintenance Issue |  | T2026.03
IPS | T2026.09 | 2025-01-08 | CLM_AM_SPC_IPS_MP_CONS_ANNOUN_MULT_BUNDLE_NATIVE | CLM_AM_SPC_IPS_MP_CN_ANC_MULB2 | Kavitha | Changing the xpath of the notification row validation | Script Fixed | Passed | Test Automation team | Script maintenance Issue | T2026.05, T2026.07, T2026.09 | T2026.03
PRE | T2026.03 | 2026-01-14 | CLM_AM_PRE_CHANGE_LOGS_IN_COMMUNICATION_CONFIGURATION_BO_NATIVE | CLM_AM_SPC_PRE_CHNG_LOG_COMCNF | Kavitha | Updated the script with adding of row in Communication in ACE473 |  | Passed | Test Automation team | Application Data Issue |  | T2026.03
PRE | T2026.03 | 2026-01-14 | CLM_AM_SPC_PRV_COMMUNICATION_CONFIG_GLOBAL_ACCNT_CONFIG_NATIVE | CLM_AM_SPC_PRV_COM_CONFIG_GBAC | Kavitha | Updated the script with adding of row in Communication in ACE473 |  | Passed | Test Automation team | Application Data Issue |  | T2026.03
IPS | T2026.03 | 2026-01-12 | CLM_AM_SPC_IPS_MASTER_PLAN_TEST_COMPLET_ACN_WAVE_NATIVE | CLM_AM_SPC_IPS_MP_TST_CMPLT_WV | Sushma | Added Execution duration and removed Planned End date. | DINC0755260 | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.03
IPS | T2026.03 | 2026-01-12 | CLM_AM_SPC_PNE_SQL_QRY_RS_CAL_NATIVE | CLM_AM_SPC_PNE_SQL_QRY_RS_CAL | Sushma | UIA_QPE: Submit for approval is disabled with message You are not authorized to change the data in DCIS page | DINC0758789 | Passed | SPC Application team | Application Bug- selector not found/disabled |  | T2026.03
IPS | T2026.03 | 2026-01-12 | CLM_AM_SPC_PNE_RISK_LETTER_EDIT_RL_STATUS_BUTTON_NATIVE | CLM_AM_SPC_PNE_RSK_LTR_AC_PL_P | Sushma | UIA_QPE: RBAM error while trying to Save Set Risk Letter Status | DINC0758826 | Passed | SPC Application team | Script maintenance Issue |  | T2026.03
IPS | T2026.03 | 2026-01-12 | CLM_AM_SPC_IPS_CR_SE_ADD_TO_MP_NATIVE | CLM_AM_SPC_IPS_CREATE_SE | Sushma | UIA_QPE: RBAM error while trying to save Master Plan. | DINC0758991 | Passed | SPC Application team | Script maintenance Issue |  | T2026.03
IPS | T2026.05 | 2026-01-12 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_SCDE_WITHIN_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WSCDE_WCMP | Sushma | UIA_QPE: Master Plan Save failed with error Downtime Reason "Others" maintained in Service Definition is not configured for Ignore CMP. | DINC0756760 | Passed | SPC Application team | Application Bug- Save fails | T2026.05 | T2026.03
IPS | T2026.03 | 2026-01-12 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_NATIVE | CLM_AM_MSTER_PLN_LNDSCAPE_CONS | Sushma | UIA_QPE: Landscape Inconsistency reason is displayed as Incorrect Scheduling Sequence instead of Multiple system in Landscape | DINC0740281 - As per the latest enhancement script changes have been completed. | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.03
IPS | T2026.03 | 2026-01-16 | CLM_AM_SPC_IPS_CR_SE_ADD_TO_MP_NATIVE | step 20 custom code with am pm | Sushma | Instead of current time, AM and PM was wrongly taken | step 20 custom code with am pm | Passed | Test Automation team | Script maintenance Issue |  | T2026.05
IPS | T2026.03 | 2026-01-15 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_NATIVE | CLM_AM_MSTER_PLN_LNDSCAPE_CONS | Sushma | Added MP_DEV2 System as part of enhancement for QPC data- to include another Dev System MP_DEV2 into the Dev Wave DCIS to prevent the "Missing System in Master Plan" error | Added MP_DEV2 System as part of enhancement for QPC data | Passed | SPC Application team | UI Enhancement by Dev |  | T2026.05
IPS | T2026.05 | 2026-01-15 | CLM_AM_SPC_SNP_SER_EXE_INCL_APS_APP_NATIVE | CLM_AM_SPC_SNP_RSC_ACP | Sushma | UIA_QPE: Under Notification History 2 entries are expected after rescheduling but only one is found. | DINC0763731 | Passed | SPC Application team | Application Data Issue |  | T2026.05
IPS | T2026.05 | 2026-01-21 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_CANCEL_SE_HOTFIX_QPC | CLM_MSTRPLN_LNDSCAPE_CONS_CAN | Sushma | UIA_QPC: Service execution status in action plan progress not moving to Cancelled after cancelling the Service Execution. | DINC0767482 | Passed | SPC Application team | Application Data Issue |  | T2026.05
IPS | T2026.05 | 2026-01-22 | CLM_AM_SPC_IPS_CR_SE_ADD_TO_MP_NATIVE | CLM_AM_SPC_IPS_ADD_SE_TO_MP | Sushma | Time format issue | Fixed time format | Passed | Test Automation team | Script maintenance Issue |  | T2026.05
IPS | T2026.05 | 2026-01-22 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_SCDE_WITHIN_CMP_DEV_QPC | CLM_AM_SPC_SNP_MP_WSCDE_WCMP | Sushma | UIA_QPE: Master Plan Save failed with error Downtime Reason "Others" maintained in Service Definition is not configured for Ignore CMP. | DINC0756760 As part of this incident developer suggestedthe Scheduling option should be chosen as 'Start anytime within next CMP after Planned Start Date Time' and not 'Start at Planned Start Date Time'. | Passed | Test Automation team | Script maintenance Issue |  | T2026.05
IPS | T2026.05 | 2026-01-15 | CLM_AM_SPC_SNP_SER_EXE_INCL_APS_APP_NATIVE | CLM_AM_SPC_SNP_RSC_ACP | Sushma | UIA_QPE: Dump error upon clicking on Action plan progress | DINC0769412 | Passed | SPC Application team | Application Dump Issue |  | T2026.05
IPS | T2026.05 | 2026-01-23 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_CANCEL_SE_HOTFIX_QPC | CLM_MSTRPLN_LNDSCAPE_CONS_CAN | Sushma | UIA_QPC: Service execution status in action plan progress not moving to Cancelled after cancelling the Service Execution. | DINC0767482-This resolved after fixing xpath. | Passed | Test Automation team | Application Bug- selector not found/disabled |  | T2026.05
ICN | T2026.07 | 2026-01-27 | CLM_AM_SPC_NOTIFICATIONS_CANCELLATION_UNPLANNED_EVENT_NATIVE | CLM_AM_NOTIF_CAN_UNAUTH_USER | Yashaswini | UIA-QPE: Getting message 'Invalid ServiceNow object ID. Please edit the event....' while create update on event - Downtime_notifications_RootCause type | DINC0772743 | Passed | SPC Application team | Application Bug- success message not available | T2026.07 | T2026.05
IPS | T2026.05 | 2026-01-23 | CLM_AM_SPC_PNE_MP_SE_START_DISTR_DATA_CENTER_TENANT_DENSITY_NATIVE | CLM_AM_SPC_PNE_MP_SE_SRT_DIS_D | Sushma | UIA_QPE: For Data centre RO2 only 5 SEs are created instead of 7 SE under MP. | DINC0773018 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | SPC Application team | Application Data Issue |  | T2026.05
CLD | T2026.09 | 2026-01-27 | CLD_FEATURE_CONNECTION_TEST | CLD_FEATURE_CONNECTION_TEST | Kavitha | UIA_QPE : Dump error in Cloud Landscape Tenants page. | DINC0772761 | Passed | SPC Application team | Application Dump Issue | T2026.07, T2026.09 | T2026.05
IPS | T2026.05 | 2026-01-21 | CLM_AM_SPC_IPS_MP_CONS_ANNOUN_MULT_BUNDLE_NATIVE | CLM_AM_SPC_IPS_MP_CN_ANC_MULB2 | Kavitha | Event ID navigation has fixed | Script fixed in QPE | Passed | Test Automation team | Script maintenance Issue |  | T2026.05
ICN | T2026.05 | 2026-01-19 | CLM_AM_SPC_NOTIF_SFSF_MASS_COM_NATIVE | CLM_AM_SPC_NOTIF_SFSF_MASS_COM | Manjula | UIA_QPE: Event with name "DO NOT USE THIS EVENT: TEST AUTOMATION EVENT" is in cancelled state | DINC0764890 | Passed | SPC Application team | Application Data Issue |  | T2026.05
ICN | T2026.05 | 2026-01-19 | CLM_AM_SPC_NOTIFICATIONS_CANCELLATION_EVENTS_NATIVE | CLM_AM_SPC_NOTIFICATIONS_CANCELLATION_EVENTS | Manjula | UIA_QPE: Not finding button "Bundle Approve and Send" | DINC0764953 | Passed | SPC Application team | Application Bug- Element not found |  | T2026.05
IAM | T2026.07 | 2026-01-27 | CLM_AM_SPC_NOTIFICATIONS_SMS_BOARD_QPE_NATIVE | CLM_AM_SPC_NOTIFICATIONS_SMS_BOARD | Manjula | UIA_QPE: System role showing as "scp_SubAccount,BYD" expecting only BYD | DINC0772572 | Passed | SPC Application team | Application Data Issue | T2026.07 | T2026.05
IPS | T2026.07 | 2026-01-29 | CLM_AM_SPC_PNE_MP_WITH_CUSTOMER_SCHEDULING_NATIVE | CLM_AM_SPC_PNE_MP_WIT_CUST_SC1 | Sushma | UIA_QPE: Life status under Action plan progress is in New status instead of Mitigated/Resolved by customer. | DINC0775950 | Passed | SPC Application team | Application Bug- Status mismatch |  | T2026.07
IPS | T2026.09 | 2026-01-29 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_CANCEL_SE_NATIVE | CLM_MSTRPLN_LNDSCAPE_CONS_CAN | Sushma | Landscape consistency check need code adjustment to create waves in the same month. Here we are creating 3 waves, tomorrow, day after and 2 days after. Now have to add a check if its month end, take the next months date or let it fail during month end. |  | Passed | Test Automation team | Application Data Issue | T2026.09 | T2026.07
IPS | T2026.09 | 2026-01-29 | CLM_AM_SPC_PNE_MASTER_PLAN_FREEZE_CREATION_NATIVE | CLM_AM_SPC_PNE_MP_CREATE_WAVES | Sushma | Landscape consistency check need code adjustment to create waves in the same month. Here we are creating 3 waves, tomorrow, day after and 2 days after. Now have to add a check if its month end, take the next months date or let it fail during month end. |  | Passed | Test Automation team | Application Data Issue | T2026.09 | T2026.07
IPS | T2026.07 | 2026-01-29 | CLM_AM_SPC_IPS_MASTER_PLAN_TEST_COMPLET_ACN_WAVE_NATIVE | CLM_AM_SPC_IPS_MP_TST_CMPLT_WV | Sushma | UIA_QPE: Upon clicking Complete button new pop up is being shown to enter the End Date | DINC0776365 | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.07
ICN | T2026.13 | 2026-02-02 | CLM_AM_SPC_NOTIFICATIONS_SUBSERVICES_NATIVE | CLM_AM_SPC_NOTIF_SUBSERVICES | Yashaswini | Updated script to refresh page by clicking on dif tabs to get internal mail buttons enabled in notification ID field | script fix | In Progress | Test Automation team | Script maintenance Issue | T2026.09, T2026.11, T2026.13 | T2026.07
ICN | T2026.07 | 2026-02-02 | CLM_AM_SPC_NOTIFICATIONS_CREATE_UPD_UNPLANNED_EVENT_NATIVE | SPC_NOTIF_CRT_UPD_UNPLAN_EVT_3 | Yashaswini | UIA-QPE: New confirmation popup for reviewing pregenerated content is seen while create update on event | DINC0778351 | Passed | SPC Application team | Application Bug- pop upText mismatch |  | T2026.07
ICN | T2026.07 | 2026-02-02 | CLM_AM_SPC_NOTIFICATIONS_FOR_MASTER_EVENT_FULL_LIFECYCLE_NATIVE | CLM_AM_SPC_NOTIF_CRT_S4_PC | Yashaswini | STEP: 'Could not start a new session. Response code 500. Message' is seen on STEP execution but locally test works fine | DINC0778737 | Passed | Start Team | Step Issue |  | T2026.07
ICN | T2026.07 | 2026-02-03 | CLM_AM_SPC_ICN_CHK_SUBSRV_FOR_PLANNED_EVENTS_NATIVE | CLM_AM_SPC_ICN_CHK_SUBS_PLN_EV | Yashaswini | Subservices with status table is not present in the internal mail | DINC0780059 | Passed | SPC Application team | Application Data Issue |  | T2026.07
ICSM | T2026.07 | 2026-02-04 | 4 Native Job | 4 Native Job | Gunjan | Clean up steps added for esclation | script fix | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
ICN | T2026.13 | 2026-02-04 | CLM_AM_SPC_NOTIF_CRT_AUTO_NOTIF_CRT_MAINTENANCE_ANNOUNCEMENT_NESTLE_NATIVE | CLM_AM_SPC_NOTIF_CRT_AUTO_ANNC | Yashaswini | START: Unable to locate and access couple of elements in the UI from START | DINC0781569 | Open/New | Start Team | Start Issue | T2026.09, T2026.11, T2026.13 | T2026.07
IPS | T2026.07 | 2026-02-05 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WITH_CMP_VAL | Sushma | Overlay button was not optional and hence test was failing | Made the step optional | Passed | Test Automation team | Application Bug- selector not found/disabled |  | T2026.07
IAM | T2026.07 | 2026-02-02 | CLM_AM_SPC_NOTIFICATIONS_SMS_BOARD_QPE_NATIVE | CLM_AM_SPC_NOTIFICATIONS_SMS_BOARD | Manjula | UIA-QPE : Exclude externally caused -Yes" is not greater than the entry where column "Exclude externally caused -NO" | DINC0778406 | Passed | SPC Application team | Application Data Issue |  | T2026.07
IPS | T2026.07 | 2026-02-05 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WITH_CMP_VAL | Sushma | UIA_QPE: Event ID not getting generated | DINC0782802 | Passed | SPC Application team | Application Dump Issue |  | T2026.07
ICN | T2026.07 | 2026-02-06 | CLM_SPC_NOTIF_MAJOR_UPGRADE_TEMPLATES_SEND_INITIAL_NOTICE_NATIVE | CLM_SPC_NOTF_MJRUP_EVTCNCL_BYD | Yashaswini | script fixed for validation of display mail | script fix | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
ICN | T2026.09 | 2026-02-09 | CLM_AM_SPC_UNLOCK_EVENT_CUSTOMER_NOTIFICATION_NATIVE | CLM_AM_SPC_UNLOCK_CUST_NOTIF | Yashaswini | UIA-QPE: Error message in 'Object Locked - Please Unlock event' popup doesn't contain 'Locking object not possible; object locked by user..' | DINC0785897 | Passed | SPC Application team | Application Bug- pop upText mismatch | T2026.09 | T2026.07
ISS | T2026.13 | 2026-02-09 | CLM_AM_SPC_SNP_SD_UI_CHANGES_FOR_INTER_SRV_CATALOG_NATIVE | CLM_AM_SPC_SNP_SD_UI_CHANGES_FOR_INTER_SRV_CATALOG_NATIVE | Hamsa | SD needs to be maintained in service now and INC20373052 is created | DINC0778824 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | In Progress | SPC Application team | Application Bug- Status mismatch | T2026.09, T2026.11, T2026.13 | T2026.07
ISS | T2026.09 | 2026-02-09 | CLM_SPC_SNP_PUBLSH_MULTIPLE_CONSUMERS_SUCCESS_NATIVE CLM_AM_SPC_SNP_LEAD_TIME_NATIVE | CLM_SPC_SNP_PUBLSH_MULTIPLE_CONSUMERS_SUCCESS_NATIVE CLM_AM_SPC_SNP_LEAD_TIME_NATIVE | Hamsa | UIA-VNS: Getting an error "User is not authenticated "when Publishis clicked | DINC0784590 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | SPC Application team | Application Bug- Status mismatch | T2026.09 | T2026.07
ISS | T2026.09 | 2026-02-09 | 4 Jobs are failing | 4 Jobs are failing | Hamsa | UIA-VNS:Getting an error " Service Definition Publish failed" When Publish clicked | DINC0787391 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | SPC Application team | Application Bug- Status mismatch | T2026.09 | T2026.07
CLD | T2026.07 | 2026-02-10 | CLM_AM_SPC_NOTIF_VERIFY_SUPPORT_PCE_FOR_TCE_NATIVE | CLM_AM_SPC_NOTIF_VERIFY_SUPPOR | Yashaswini | UIA-QPE: Dump error is seen on clicking notify selected system in cloud landscape> system | DINC0787665 | Passed | SPC Application team | Application Dump Issue |  | T2026.07
IES | T2026.07 | 2026-02-06 | CLM_AM_SPC_IES_SAVE_POPUP_LOGICAL_PRODUCT_LIST_OIF_DEV_QPC | CLM_AM_SPC_IES_SV_POP_LG_PRDL | Kavitha | UIA_QPC: In Availability Management, Logical Product List page QPC3 is not in In Preparation, Active, or Obsolete state. | DINC0784122 | Passed | SPC Application team | Oberon5 UI Issue |  | T2026.07
IES | T2026.09 | 2026-02-10 | CLM_AM_SPC_PNE_4EYE_CHECK_NATIVE | CLM_AM_SPC_PNE_4EYE_CHECK1 | Kavitha | UIA_QPE: In 4eye check page after clicking on Approve 4 eye check button, in "AI Generated - Recommendation Summary" popup one mandatory dropdown field we can see. because of this not able to Edit. | DINC0786039 | Passed | SPC Application team | UI Enhancement by Dev | T2026.09 | T2026.07
IES | T2026.09 | 2026-02-10 | CLM_AM_SPC_IES_4EYE_CHECK_SE_WITH_TICKET_GENAI_NATIVE | CLM_AM_SPC_IES_4EYE_CHK_SE_TKT | Kavitha | UIA_QPE: In 4eye check page after clicking on Approve 4 eye check button, in "AI Generated - Recommendation Summary" popup one mandatory dropdown field we can see. because of this not able to Edit. | DINC0786039 | Passed | SPC Application team | Oberon5 UI Issue | T2026.09 | T2026.07
IES | T2026.07 | 2026-02-10 | CLM_AM_SPC_PNE_EXE_WRF_MULT_SE_FOR_TKT_NATIVE | CLM_AM_SPC_PNE_EX_WF_MUL_SE_T2 | Kavitha | Added Cancellation reason category steps in cancellation of SE | Script fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
ICN | T2026.09 | 2026-02-10 | CLM_AM_SPC_NOTIF_CUSTOMER_VS_BONUS_PLAN_NATIVE | CLM_SPC_NOTIF_CUST_VS_BONUSPLN | Yashaswini | UIA-QPE: Availability in percentage for exclude externally caused and not exclude externally caused are equal which is expected to be greater | DINC0787730 | Passed | SPC Application team | Application Data Issue | T2026.09 | T2026.07
IPS | T2026.07 | 2026-01-29 | CLM_AM_SPC_IPS_MP_CONS_ANNOUN_MULT_BUNDLE_HOTFIX_QPC | CLM_AM_SPC_IPS_MP_CN_ANC_MULB2 | Kavitha | Updated the xpaths for notification id validation in second tab | Script fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
PRE | T2026.07 | 2026-02-02 | CLM_AM_SPC_PROV_ENABL_APPL_PARAM_TEMPL_BO_NATIVE | PARAMETER_EXISTING_TEMPLATE | Kavitha | Replaced error validation custom code with check variable | Script fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
PRE | T2026.07 | 2026-02-02 | CLM_AM_PRE_CHANGE_LOGS_IN_COMMUNICATION_CONFIGURATION_BO_NATIVE | CLM_AM_SPC_PRE_CHNG_LOG_COMCNF | Kavitha | Replaced current dattime validation custom code with $TODAY variable | Script fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
PRE | T2026.07 | 2026-02-02 | CLM_AM_PRE_CHANGE_LOGS_IN_COMMUNICATION_CONFIGURATION_BO_NATIVE | CLM_AM_SPC_PRE_CHNG_LOG_COMCNF | Kavitha | Used QPE and QPC variables instead of custom codes | Script fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.07
IPS | T2026.09 | 2026-02-10 | CLM_AM_SPC_IPS_MASTER_PLAN_TEST_COMPLET_ACN_WAVE_HOTFIX_QPC | CLM_AM_SPC_IPS_MP_TST_CMPLT_WV | Sushma | UIA_QPE/QPC: Product Update field is found instead of Release version field while creating Wave | DINC0787951 | Passed | Test Automation team | UI Enhancement by Dev | T2026.09 | T2026.07
ICSM | T2026.09 | 2026-02-24 | CLM_AM_SPC_SNP_PAE_FROM_PAD_VIA_API_NATIVE | CLM_SPC_SNP_PAE_FROM_PAD_API | Gunjan | UIA-QPE: Lifecycle status of operation plan hasn't changed from Inactive to Completed. | DINC0803595 | Passed | Test Automation team | Application Bug- Status mismatch | T2026.09 | T2026.09
PDE | T2025.11 | 2025-03-11 | CID_3359_CLM_AM_COM_ADT_SERVICE_CATALOG_PROCESS_DEFINITION_INTEG_SPC_COM | CID_3359_CLM_AM_COM_ADT_SERVICE_CATALOG_PROCESS_DEFINITION_INTEG_SPC_COM | Divya | Error message displayed in Note | Application Issue | Passed | SPC Application team | UI Change Issue |  | T2025.11
DRE | T2025.11 | 2025-03-11 | COM_DDI_DRE_CREATE_RECEIVER_AND_VALIDATE_THE_CREATED_RECEIVER_UNDER_VERSIONS_APP | COM_DDI_DRE_CREATE_RECEIVER_AND_VALIDATE_THE_CREATED_RECEIVER_UNDER_VERSIONS_APP | Divya | No results displayed in search List - Application UI Issue | DINC0445926 | Open/New | SPC Application team | UI Change Issue |  | T2025.11
DIS | T2025.11 | 2025-03-11 | CID_1483_DDI_DIS_CREATE_DISTRIBUTION_VIA_DISTRIBUTION_APP | CID_1483_DDI_DIS_CREATE_DISTRIBUTION_VIA_DISTRIBUTION_APP | Divya | Not able to fetch Distribution ID | Script Fix | In Progress | Test Automation team | Script maintenance Issue |  | T2025.11
DDV | T2025.11 | 2025-03-12 | CID_1955_DDI_DDV_VALIDATE_REFRESH_REMOTE_SOURCE | CID_1955_DDI_DDV_VALIDATE_REFRESH_REMOTE_SOURCE | Divya | No results displayed in search List - Application UI Issue | DINC0445926 | Open/New | SPC Application team | UI Change Issue |  | T2025.11
TEX | T2025.13 | 2025-03-19 | ART_TEX_REGRESSION | All | Divya | App could not be opened in A2E | DINC0445976 | Passed | SPC Application team | Application Bug |  | T2025.13
TEX | T2025.13 | 2025-03-19 | CID_3391_CLM_AM_COM_PROCESS_DEF_REMOTE_PROCESS_LOG_INTEG_TEST | CID_3391_CLM_AM_COM_PROCESS_DEF_REMOTE_PROCESS_LOG_INTEG_TEST | Gunjan | After clicking on START button application not navigating to A2Q | Script Fix | Passed | Test Automation team | Script maintenance Issue |  | T2025.13
TEX | T2025.13 | 2025-03-26 | COM_ART_TEX_COMPLETE_APPROVE_ADDNOTE_ABORT_SETTOERROR | COM_ART_TEX_COMPLETE_APPROVE_ADDNOTE_ABORT_SETTOERROR | Divya | UIA-A2E: Approve Task Execution not successful | DINC0452566 | Passed | SPC Application team | Application Bug |  | T2025.13
DDE | T2025.13 | 2025-03-26 | CID_1482_DDI_DDE_CREATE_AND_DELETE_LOCAL_DEFINITION | CID_1482_DDI_DDE_CREATE_AND_DELETE_LOCAL_DEFINITION | Divya | No results displayed in A2E - Enhancement done | Script Enhancement - Clear filters before searching the definition ID | Passed | Test Automation team | Script maintenance Issue |  | T2025.13
CLD | T2025.17 | 2025-04-15 | STEP issue for COM_ART_TEX_REGRESSION |  | Gunjan | STEP: Incorrect Success Count is getting displayed for COM_ART_TEX_REGRESSION module. | DINC0472565 | Passed |  | Step Issue
ICN | T2026.05 | 2026-01-27 | CLM_AM_SPC_NOTIF_SFSF_MASS_COM_NATIVE | CLM_AM_SPC_NOTIF_SFSF_MASS_COM | Yashaswini | Fixed the script for picking the newly created bundle and event | script fixed | In Progress | Test Automation team | Script maintenance Issue |  | T2026.05
ICN | T2026.05 | 2026-01-27 | CLM_SPC_NOTIF_MAJOR_UPGRADE_TEMPLATES_SEND_INITIAL_NOTICE_NATIVE | CLM_SPC_NOTF_MJR_UPTMP_EVTCRT2 | Yashaswini | script fixed for preview internal mail validation changes | script fixed | In Progress | Test Automation team | Script maintenance Issue |  | T2026.05
ISS | T2026.05 | 2026-01-27 | 13 Jobs are failing QPE | 13 Jobs are failing in qpe | Hamsa | UIA-QPE: Certificate UIA_TKT_API_NEW is expired. | DINC0772173 | Passed | SPC Application team | Application Data Issue |  | T2026.05
ISS | T2026.05 | 2026-01-26 | CLM_AM_SPC_SNP_FEEDBACK_TEMPLATE_USAGE_CODE_FIELD_CHECK_SE_RISK_ASSESS_HOTFIX_QPC | CLM_AM_SPC_SNP_FEEDBACK_TEMPLATE_USAGE_CODE_FIELD_CHECK_SE_RISK_ASSESS_HOTFIX_QPC | Hamsa | UIA-QPC: After clicking on ask AI on risk Assessment tab, AI Proposed Risk Level filed is blank. | DINC0766223 | Passed | SPC Application team | Application Bug- Text mismatch |  | T2026.05
IPS | T2026.05 | 2026-01-27 | CLM_AM_SPC_PNE_MP_SE_START_DISTR_DATA_CENTER_TENANT_DENSITY_NATIVE | CLM_AM_SPC_PNE_MP_SE_SRT_DIS_D | Sushma | UIA_QPE: For Data centre RO2 only 5 SEs are created instead of 7 SE under MP. | DINC0773018 | Passed | Test Automation team | Application Data Issue |  | T2026.05
ICN | T2026.09 | 2026-02-16 | CLM_AM_SPC_ICN_CHK_SUBSRV_FOR_PLANNED_EVENTS_NATIVE | CLM_AM_SPC_ICN_CHK_SUBS_PLN_EV | Yashaswini | Subservices with status table is not present in the internal mail | DINC0780059 | Passed | Test Automation team | Script maintenance Issue |  | T2026.09
IPS | T2026.09 | 2026-02-12 | CLM_AM_SPC_SNP_MASTER_PLAN_CANCELLATION_SCENARIO_NATIVE | CLM_AM_SNP_MP_CAN_WAV_SKIP_NOT | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_IPS_MASTER_PLAN_TEST_COMPLET_ACN_WAVE_HOTFIX_QPC | CLM_AM_SPC_IPS_MP_TST_CMPLT_WV | Sushma | Enhancement | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_SNP_MASTER_PLAN_CHANGE_SCHEDULE_SD_PARAMETERS_NATIVE | CLM_SPC_MSTR_PLN_CN_SCH_PAR_SD | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_SCDE_WITHIN_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WSCDE_WCMP | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_withoutSCDE_nonCMP_NATIVE | CLM_AM_SPC_SNP_MP_WOSCDE_NOCMP | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_SNP_MASTER_PLAN_CHANGE_SCHEDULE_SD_PARAMETERS_NATIVE | CLM_SPC_MSTR_PLN_CN_SCH_PAR_SD | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_DISABLE_CUST_NOTIFICATION_NATIVE | MASTER_PLAN_DISABLE_CUST_NOT | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WITH_CMP | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2025.51 | 2026-02-11 | For all edit case with auto execution ticked while recording, recording panel is not being displayed for latest START version |  | Sushma | START: Recording panel is not being displayed while modifying the test script while recording. | DINC0789753 | Passed | SPC Application team | Start Issue |  | T2026.09
IPS | T2026.09 | 2026-02-12 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_TENANT_NATIVE | CLM_AM_SPC_SNP_MP_TENANT_CANC1 | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_SNP_SER_EXE_INCL_APS_APP_NATIVE | CLM_AM_SPC_SNP_SER_EXE_INCL_APS_APP_NATIVE | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_SNP_MP_UPDT_NOTIF_NATIVE | CLM_AM_SNP_UPDT_NOTIF_MP_WAVE | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_DELAY_STRETCH_PROCESS_START_NATIVE | CLM_MST_PLN_DELY_STRCH_PRO_STR | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_SNP_MASTER_PLAN_DYN_DT_DURATION_NATIVE | CLM_AM_SPC_SNP_MASTER_PLAN | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-13 | CLM_AM_SPC_SNP_MASTER_PLAN_CHK_ONLINE_DEPLOYABLE_NATIVE | CLM_AM_SPC_SNP_MSTR_ONLINE_DEP | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_PNE_MP_NTIF_EVT_CRT_NATIVE | CLM_AM_SPC_MP_ISL_NTIF_EVT_CRT | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-16 | CLM_AM_SPC_PNE_MASTER_PLAN_VIA_GAF_NATIVE | CLM_SPC_PNE_MASTR_PLAN_VIA_GAF | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-17 | CLM_AM_SPC_PNE_MP_PVT_DPL_ANC2_NATIVE | CLM_AM_SPC_PNE_MP_DCIS_ADD_RM | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-17 | CLM_AM_SPC_PNE_MASTER_PLAN_VIA_GAF_INVALID_FILE_UPLOAD_NATIVE | CLM_SPC_PNE_INVALD_MP_VIA_GAF | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-17 | CLM_AM_SPC_PNE_WAVE_NOT_CANCELLED_UNTIL_PLANNED_START_TIME_NATIVE | CLM_AM_SPC_WAVE_NOCAN_STILDATE | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-18 | CLM_AM_SPC_PNE_MP_RESCHEDULE_DOWNTIME_END_TIME_NATIVE | CLM_AM_SPC_PNE_MP_RSCH_DN_ENT | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-18 | CLM_AM_SPC_PNE_MP_SE_START_DISTR_DATA_CENTER_TENANT_DENSITY_NATIVE | CLM_AM_SPC_PNE_MP_SE_SRT_DIS_D | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-18 | CLM_AM_SPC_SNP_MASTER_PLAN_ENABLE_CUSTOMER_NOTIFICATION_NATIVE | CLM_SPC_MSTR_PLN_CUST_NOTIF_EN | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-18 | CLM_AM_SPC_PNE_MP_VIA_GAF_COMMON_PROCESS_PARAMETER_NATIVE | CLM_AM_SPC_PNE_MP_VIA_GAF_COMM | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-18 | CLM_AM_SPC_PNE_MP_WITH_CUSTOMER_SCHEDULING_NATIVE | CLM_AM_SPC_PNE_MP_WIT_CUST_SCH | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2025.51 | 2026-02-18 | CLM_AM_SPC_PNE_SQL_QRY_RS_CAL_NATIVE | CLM_AM_SPC_PNE_SQL_QRY_RS_CAL | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | SPC Application team | Application Bug- Status mismatch |  | T2025.51
IPS | T2026.09 | 2026-02-19 | CLM_AM_SPC_PNE_RISK_LETTER_GEN_NATIVE | CLM_AM_SPC_PNE_RISK_LETER_GEN1 | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-19 | CLM_AM_SPC_PNE_RISK_LETTER_EDIT_RL_STATUS_BUTTON_NATIVE | CLM_AM_SPC_PNE_RSK_LTR_AC_PL_P | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-19 | CLM_AM_SPC_PNE_RISK_LETTER_SYNC_RL_STS_ON_NEW_ACTION_PLAN_PROGRESS_CRTE_NATIVE | CLM_AM_SPC_PNE_RSK_LTR_AC_PL_P | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-19 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_NATIVE | CLM_AM_MSTER_PLN_LNDSCAPE_CONS | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-19 | CLM_AM_SPC_PNE_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_CANCEL_SE_NATIVE | CLM_MSTRPLN_LNDSCAPE_CONS_CAN | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-20 | CLM_AM_SPC_PNE_MASTER_PLAN_FREEZE_CREATION_NATIVE | CLM_AM_SPC_PNE_MP_FRZ_PRE_REQ | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2025.51 | 2026-02-20 | CLM_AM_SPC_IPS_MASTER_PLAN_LNDSCAP_CONSISTNCY_CHCK_WITH_SD_NATIVE | CLM_SPC_IPS_MP_LND_CNS_CHK_SD | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | SPC Application team | Application Bug- Status mismatch |  | T2026.09
IPS | T2026.09 | 2026-02-20 | CLM_AM_SPC_PNE_MP_NOTIF_WITH_MULTIPLE_BUNDLE_NATIVE | CLM_AM_SPC_PNE_MP_NOTF_ML_BND1 | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-20 | CLM_AM_SPC_SNP_MASTER_PLAN_SEND_CONSOLIDATED_ANNOUNCEMENT_NATIVE | CLM_AM_SPC_CRT_MP_CN1 | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2026.09 | 2026-02-23 | CLM_AM_SPC_IPS_MASTER_PLAN_LNDSCAPE_CONSISTENCY_CHECK_WITH_SCHEDULING_OPTION_START_AT_CMP_NATIVE | CLM_AM_SPC_PNE_MSTR_PLN_LSC_CO | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2025.51 | 2026-02-23 | CLM_AM_SPC_IPS_DEFAULT_MP_TEXT_NATIVE | CLM_AM_SPC_IPS_DEFAULT_MP_TEXT | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | SPC Application team | Application Bug- Status mismatch |  | T2026.09
IPS | T2026.09 | 2026-02-23 | CLM_AM_SPC_IPS_MP_CONS_ANNOUN_MULT_BUNDLE_NATIVE | CLM_AM_SPC_IPS_MP_CN_ANC_MBCL1 | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.09
IPS | T2025.51 | 2026-02-24 | CLM_AM_SPC_IPS_MASTER_PLAN_TEST_COMPLET_ACN_WAVE_NATIVE | CLM_AM_SPC_IPS_MP_TST_CMPLT_WV | Sushma | Master plan Enhancement Script adaptation | Script Fixed | Passed | SPC Application team | Application Bug- Status mismatch |  | T2026.09
ICN | T2026.09 | 2026-02-13 | CLM_AM_SPC_ICN_IMPACT_REASSESSMENT_BUNDLE_IDENTIFICATION_PHASE | CLM_AM_SPC_ICN_IMPACT_REASSESSMENT_BUNDLE_IDENTIFICATION_PHASE | Manjula | UIA_QPE : Event unlock is not happening | DINC0792672 | Passed | SPC Application team | Application Bug- Locking object Error |  | T2026.09
IAM | T2026.11 | 2026-02-16 | CLM_AM_SPC_NOTIF_VERIFY_SUPPORT_PCE_FOR_TCE_NATIVE | CLM_AM_SPC_NOTIF_VERIFY_SUPPORT | Manjula | UIA-QPE: Created event is not found in notification > aggregation view | DINC0794467 | Passed | SPC Application team | Application Data Issue | T2026.11 | T2026.09
IAM | T2026.09 | 2026-02-20 | CLM_AM_SPC_NOTIF_FOR_CODE_BLUE_NATIVE | CLM_AM_SPC_NOTIF_FOR_CODE_BLUE | Manjula | UIA_QPE : Mass communication code blue event status is "in progress" not updating to "successfully sent" | DINC0799865 | Passed | SPC Application team | Application Data Issue |  | T2026.09
IPS | T2025.51 | 2026-02-23 | CLM_AM_SPC_IPS_MP_COMPLETE_API_VNS_NATIVE | CLM_AM_SPC_IPS_MP_APPROVE_API | Sushma | UIA_VNS: Master plan not moving to approved status in VNS system after Approve API has been called. | DINC0802606 | Open/New | SPC Application team | Application Bug- Status mismatch |  | T2026.09
ICN | T2026.09 | 2026-02-24 | CLM_AM_SPC_NOTIFICATION_FROM_CLD_TENANT_NATIVE | CLM_AM_NOTIF_CLD_TENANT | Yashaswini | UIA-QPE: Dump error is seen when clicked on preview customer email and preview internal mail in notification creation popup | DINC0803168 | Passed | SPC Application team | Application Dump Issue |  | T2026.09
CLD | T2026.09 | 2026-02-10 | CLD_CLDIS_ACCESS_TEST_NATIVE | CLD_CLDIS_VERIFY_ACCESS | Kavitha | Updated the xpath for the row | Script Fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.09
CLD | T2026.09 | 2026-02-20 | CLM_AM_SPC_CLD_INTERNAL_CONTACT_CREATION_DELETION_NATIVE | CLM_SPC_CLD_INTCONT_ENTITY_CRT | Kavitha | UIA_QPE: There is no C5012995 User ID and Name Nakott, Dirk' in UI. | DINC0799868 | Passed | SPC Application team | Application Data Issue |  | T2026.09
ROT | T2026.13 | 2026-02-24 | CLM_AM_SPC_CREATE_APPROVE_ABORT_PROCESS_HOTFIX_QPC | CLM_AM_SPC_CRT_APRV_ABRT_PROC | Kavitha | UIA_QPC: The status of the Automation runtime demo process is expected Action required but showing Error status. | DINC0801706 | In Progress | SPC Application team | Application Bug- Status mismatch | T2026.11, T2026.13 | T2026.09
ISS | T2026.05 | 2026-02-24 | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | Hamsa | UIA-QPE: Search results are displaying no records on service execution screen for name "SNP: For UI Automation- Automatic Popup check for difference in queues | DINC0803598 ¦ | In Progress | SPC Application team | Application Data Issue |  | T2026.09
IES | T2026.05 | 2026-02-24 | CLM_AM_SPC_PNE_EXE_WRF_MULT_SE_FOR_TKT_DEV_QPC | CLM_AM_SPC_PNE_EX_WF_MUL_SE_T3 | Kavitha | UIA_QPC: When cancelling the service execution after creating it, I am getting this error message: “The domain is not trusted. Please contact the administrator.” | DINC0803824 | Open/New | SPC Application team | Application Bug- User auth error |  | T2026.09
ICSM | T2026.11 | 2026-03-02 | CLM_AM_SPC_SNP_PAE_FROM_PAD_VIA_API_NATIVE | CLM_SPC_SNP_PAE_FROM_PAD_API | Gunjan | UIA-QPE: Service Execution ID is not getting generated after hitting API request and getting status as 400 instead of 200. | DINC0810071 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | Test Automation team | Application Bug- Status mismatch |  | T2026.11
ICN | T2026.11 | 2026-03-02 | CLM_AM_SPC_NOTIF_AUT_NTF_FR_S4_NATIVE | CLM_AM_SPC_NOTIF_AUTO_NTF_S4 | Yashaswini | Active execution status shows error instead of completed in 'Service Execution: S4: Automated Customer Notifications' page | DINC0810203 | Passed | SPC Application team | Application Bug- Status mismatch |  | T2026.11
ISS | T2026.11 | 2026-03-02 | CP | CP | Yashaswini | UIA-SAP4ME: User validity expired and unable to login to the app | DINC0810116 | Passed | SPC Application team | Application Bug- User auth error |  | T2026.11
IPS | T2026.11 | 2026-03-02 | CLM_AM_SPC_IPS_MP_START_API_NATIVE | CLM_AM_SPC_IPS_MP_CRAPST_API | Sushma | UIA_VNS: Master plan not moving to approved status in VNS system after Approve API has been called. | Script Fixed | Passed | SPC Application team | Application Data Issue |  | T2026.11
IPS | T2026.11 | 2026-03-02 | CLM_AM_SPC_IPS_MP_COMPLETE_API_VNS_NATIVE | CLM_AM_SPC_IPS_MP_COMPLETE_API | Sushma | UIA_VNS: Master plan not moving to approved status in VNS system after Approve API has been called. | Script Fixed | Passed | SPC Application team | Application Data Issue |  | T2026.11
IPS | T2026.11 | 2026-03-02 | CLM_AM_SPC_IPS_MP_APPROVE_API_VNS_NATIVE | CLM_AM_SPC_IPS_MP_APPROVE_API_VNS_NATIVE | Sushma | UIA_VNS: Master plan not moving to approved status in VNS system after Approve API has been called. | Script Fixed | Passed | SPC Application team | Application Data Issue |  | T2026.11
IAM | T2026.11 | 2026-03-02 | CLM_AM_SPC_NOTIF_CUSTOMER_VS_BONUS_PLAN_NATIVE | CLM_AM_SPC_NOTIF_CUSTOMER_VS_BONUS | Manjula | UIA-QPE : Exclude externally caused -Yes" is not greater than the entry where column "Exclude externally caused -NO" | DINC0810215 | Passed | SPC Application team | Application Data Issue |  | T2026.11
IAM | T2026.11 | 2026-03-02 | CLM_AM_SPC_NOTIF_FOR_CODE_BLUE_NATIVE 10 Jobs | CLM_AM_SPC_NOTIF_FOR_CODE_BLUE | Manjula | UIA_QPE: Seeing new pop up after clicking on Send notification for code blue events | DINC0810174 | Passed | SPC Application team | Application Bug- pop upText mismatch |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_FOR_CODE_BLUE_NATIVE | CLM_AM_SPC_NOTIF_CB_GNL | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_CBE_CONTACT_GROUP_6_FINAL_CHECK_NATIVE | CLM_AM_SPC_NOTIF_CNT_G4_OVRWRT | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_CBE_INDIVIDUAL_USER_4_NOTIF_SEND_FINAL_CHEC_NATIVE | CLM_AM_SPC_NOTIF_CB_CNTCT_GP6 | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_CB_TARGET_COMM_INITIAL_NOTICE_CHECKS_NATIVE | CLM_AM_SPC_NOTIF_CB_IU_FNLCHK | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_CB_BTN_CHK_BP_NATIVE | CLM_AM_SPC_NOTIF_CB_COM_INT_CH | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2026-03-05 | CLM_AM_SPC_NOTIF_CB_TRGET_COMM_FIELD_CHECKS_NATIVE | CLM_AM_SPC_NOTIF_CB_ADD_BP_VAL | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2025-03-06 | CLM_AM_SPC_NOTIF_CB_TARGET_COMM_MISSING_ISSUE_CHECK_NATIVE | CLM_AM_SPC_NOTIF_CB_TCOM_INCHK | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2025-03-06 | CLM_AM_SPC_NOTIF_CB_TARGET_COMM_MISSING_INFO_CHECK_NATIVE | CLM_AM_SPC_NOTF_CB_MIS_ISUECHK | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2025-03-06 | CLM_AM_SPC_NOTIF_CB_TARGET_COMM_CONCLUSION_NOTIF_CHECKS | CLM_AM_SPC_NOTIF_CB_TRGT_COMM1 | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2025-03-06 | CLM_AM_SPC_NOTIF_CB_TARGET_COMM_UPDATE_NOTIF_CHECKS | CLM_AM_SPC_NOTIF_CB_COM_INT_CH | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IAM | T2026.11 | 2025-03-06 | CLM_AM_SPC_NOTIF_CB_SAP4MEREPLICATION_NATIVE | CLM_AM_SPC_NOTIF_CB_SAP4RP_MC1 | Manjula | New pop up enhancement script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
IPS | T2026.11 | 2025-03-06 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE | CLM_AM_SPC_SNP_MP_WITH_CMP_VAL | Sushma | Login screen was displayed after clicking on event id link | Script Fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.11
IPS | T2026.13 | 2025-03-06 | CLM_AM_SPC_PNE_MP_NTIF_EVT_CRT_NATIVE | CLM_AM_SPC_MP_ISL_NTF_EVT_CR_1 | Sushma | Login screen was displayed after clicking on event id link | Script Fixed | Passed | Test Automation team | Script maintenance Issue | T2026.13 | T2026.11
IES | T2026.11 | 2026-03-10 | CLM_SPC_PNE_EXEWRF_FULLY_AUTOMATED_TEST_HOTFIX_QPC and 7 jobs | CLM_SPC_PNE_EXEWRF_FULLY_AUTOM | Kavitha | UIA_QPC: There is a Dump error in monitoring tickets page. | DINC0818651 | Passed | SPC Application team | Application Dump Issue |  | T2026.11
IES | T2026.11 | 2026-02-27 | CLM_AM_SPC_TIME_RECORDING_HOTFIX_QPC and 9 jobs | CLM_AM_SPC_TIME_RECORDING | Kavitha | UIA_QPC: When cancelling the service execution after creating it, I am getting this error message: “The domain is not trusted. Please contact the administrator.” | DINC0803824 | Passed | SPC Application team | Application Bug- User auth error |  | T2026.11
IES | T2026.11 | 2026-03-02 | CLM_AM_SPC_IES_SAVE_POPUP_LOGICAL_PRODUCT_LIST_OIF_DEV_QPC | CLM_AM_SPC_IES_SV_POP_LG_PRDL | Kavitha | Dropdown is not visible so make that step as optional rest all teh steps worked fine | Script Fixed | Passed | Test Automation team | Script maintenance Issue |  | T2026.11
ICSM | T2026.11 | 2026-03-10 | 6 Jobs in QPC | 6 Jobs in QPC | Gunjan | UIA-QPC: Dump error on Service Execution page | DINC0818745 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | SPC Application team | Application Dump Issue | T2026.11 | T2026.11
ISS | T2026.11 | 2026-03-10 | Many jobs in QPC failed | Many jobs in QPC failed | Hamsa | UIA-QPC: Dump error on Service Execution page | DINC0818745 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Passed | SPC Application team | Application Dump Issue |  | T2026.11
ISS | T2026.11 | 2026-03-10 | CLM_AM_SPC_SNP_REG_SPECIFIC_NATIVE | CLM_AM_SPC_SNP_REG_SPECIFIC_NATIVE | Hamsa | new Pop up script adaption | Script Fixed | Passed | Test Automation team | UI Enhancement by Dev |  | T2026.11
ISS | T2026.13 | 2026-03-02 | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | Hamsa | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | DINC0803598 ¦ | Passed | SPC Application team | Application Data Issue | T2026.13 | T2026.11
ITSM | T2026.13 | 2026-03-02 | CLM_SPC_ITSM_ASKAI_FEATURES_NATIVE | CLM_SPC_ITSM_ASKAI_SOL_SEARCH | Divya | UIA-QPE: Error displays 'No authorization to access the Intelligent Search' on ASK AI - Solution Search page | DINC0816094 | Open/New | SPC Application team | Application Bug- User auth error | T2026.13 | T2026.11
IPS | T2026.11 | 2026-03-10 | 10 jobs dump issue in MP page | 10 jobs dump issue in MP page | Sushma | 10 jobs dump issue in MP page | DINC0818875 | Passed | SPC Application team | Application Dump Issue |  | T2026.11
ICN | T2026.13 | 2026-03-11 | CLM_AM_SPC_NOTIF_CLOSE_REOPEN_EVENTS_NATIVE | CLM_AM_SPC_NOTIF_CLOSE_REOPEN_EVENTS_NATIVE | Yashaswini | UIA-QPE: Error during closing event ' You are not authorized to close the event QPE5113332. Please refer to FAQ' | DINC0820038 | Passed | SPC Application team | Application Bug- Save fails | T2026.13 | T2026.11
ICN | T2026.13 | 2026-03-11 | CLM_AM_SPC_NOTIFICATIONS_CANCELLATION_UNPLANNED_EVENT_NATIVE | CLM_AM_NOTIF_CAN_UNAUTH_USER | Yashaswini | Cancel event error message for unauthorized access is changed to 'You are not authorized to cancel the event QPE5110175. Please refer to FAQ' | DINC0820053 | Passed | SPC Application team | Application Bug- error message not available | T2026.13 | T2026.11
ICN | T2026.13 | 2026-03-11 | CLM_AM_SPC_NOTIFICATIONS_CLOSE_CUSTOMER_COMMUNICATION_EVENT_NATIVE | CLM_AM_SPC_NOTIFICATIONS_CLOSE_CUSTOMER_COMMUNICATION_EVENT_NATIVE | Yashaswini | UIA-QPE: Getting you are not authorized to reopen event error for UIA_POWER2 user | DINC0820060 | Passed | SPC Application team | Application Bug- error message not available | T2026.13 | T2026.11
IPS | T2026.13 | 2026-03-11 | 3 jobs dump issue in MP page | 3 jobs dump issue in MP page | Sushma | 3 jobs dump issue in MP create using wizard | DINC0820068 | Passed | SPC Application team | Application Dump Issue | T2026.13 | T2026.11
ICN | T2026.13 | 2026-03-12 | CLM_AM_SPC_ICN_IMPACT_REASSESSMENT_BUNDLE_RESOLUTION_PHASE | CLM_AM_SPC_ICN_IMPACT_REASSESSMENT_BUNDLE_RESOLUTION_PHASE | Manjula | UIA_QPE: Start date and End date is not showing for impact reassessment | DINC0822009 | Passed | SPC Application team | Application Data Issue |  | T2026.13
ITSM | T2026.13 | 2026-03-13 | CLM_AM_SPC_ITSM_TICKET_REFERENCES_ASSIGN_DEV_QPC | CLM_ITSM_TKT_REF_ASN_DTIME_REC | Divya | UIA-QPC: No records displayed for downtime records under Add References | DINC0822669 | Open/New | SPC Application team | Application Data Issue |  | T2026.13
IES | T2026.13 | 2026-03-23 | CLM_AM_SPC_PNE_MULTI_SBC_CREATE_TKT_SE_NATIVE | CLM_AM_SPC_PNE_MULTI_SBC_CLEAN | Kavitha | Re-recorded the value help button | Script Fixed | Passed | Test Automation team | Script maintenance Issue | T2026.13
IES | T2026.13 | 2026-03-18 | CLM_AM_SPC_IES_EXCEL_UPLOAD_IN_LPR_NATIVE | CLM_AM_SPC_IES_EXCEL_UPLOAD_IN | Kavitha |  | Script Fixed | Passed | Test Automation team | Script maintenance Issue | T2026.13
ISS | T2026.13 | 2026-03-18 | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | CLM_AM_SPC_SNP_ABANDON_SERVICE_NATIVE | Hamsa | Testdata updated | Script Fixed | Passed | Test Automation team | Application Data Issue | T2026.13 | T2026.13
ISS | T2026.13 | 2026-03-18 | CLM_AM_SPC_SNP_CDM_CAPACITY_DEMAND_MATCHING_NATIVE | CLM_AM_SPC_SNP_CDM_CAPACITY_DEMAND_MATCHING_NATIVE | Hamsa | xpath updated | Script Fixed | Passed | Test Automation team | Script maintenance Issue | T2026.13 | T2026.13
ISS | T2026.13 | 2026-03-24 | CLM_AM_SPC_SNP_FINAL_SER_EXE_NATIVE | CLM_AM_SPC_SNP_FINAL_SER_EXE_NATIVE | Hamsa | UIA-QPE: Search results are displaying no records on service execution screen for name "Copy - Unlock or Reset Application Administration User" | DINC0833485 ¦ CSM/FSM Configurable Workspace ¦ ServiceNow | Open/New | SPC Application team | Application Data Issue | T2026.13 | T2026.13
IPS | T2026.13 | 2026-03-24 | CLM_AM_SPC_SNP_MASTER_PLAN_CANCELLATION_SCENARIO_NATIVE |  | Sushma | UIA_QPE: Upon clicking on Notify customer button, Notification Sub Type does not have announcement option | DINC0833862 | Passed | SPC Application team | Application Data Issue |  | T2026.13
IPS | T2026.13 | 2026-03-24 | CLM_AM_SPC_SNP_MASTER_PLAN_WITH_CMP_NATIVE |  | Sushma | UIA_QPE: Upon clicking on Notify customer button, Notification Sub Type does not have announcement option | DINC0833862 | Passed | SPC Application team | Application Data Issue |  | T2026.13
IPS | T2026.13 | 2026-03-24 | CLM_AM_SPC_SNP_MASTER_PLAN_ENABLE_CUSTOMER_NOTIFICATION_NATIVE |  | Sushma | UIA_QPE: Upon clicking on Notify customer button, Notification Sub Type does not have announcement option | DINC0833862 | Passed | SPC Application team | Application Data Issue |  | T2026.13
IPS | T2026.13 | 2026-03-24 | CLM_AM_SPC_PNE_MASTER_PLAN_VIA_GAF_NATIVE |  | Sushma | UIA_QPE: Excel upload failing with error File was not successfully processed. Re-upload a consistent excel. | DINC0833747 | Passed | SPC Application team | Application Bug- Save fails |  | T2026.13
IPS | T2026.13 | 2026-03-24 | CLM_AM_SPC_PNE_MASTER_PLAN_VIA_GAF_INVALID_FILE_UPLOAD_NATIVE |  | Sushma | UIA_QPE: Excel upload failing with error File was not successfully processed. Re-upload a consistent excel. | DINC0833747 | Passed | SPC Application team | Application Bug- Save fails |  | T2026.13
ICN | T2026.13 | 2026-03-23 | CLM_AM_SPC_NOTIFICATIONS_CLOSE_FREESTYLE_EVENT_NATIVE | CLM_AM_SPC_NOTIFICATIONS_CLOSE_FREESTYLE_EVENT_NATIVE | Yashaswini | Don't have authorization to perform Reopen operation. Please refer to FAQ, raised to security team to provide auth | DINC0832075 | Open/New | SPC Application team | Application Bug- User auth error |  | T2026.13

## SPC Categorization
Module | (All)
Initial Takts | T2025.51
Row Labels | Count of Category
Script maintenance Issue | 4
UI Change Issue | 3
Grand Total | 7

## Dropdown values
Takt | Module | Analyzer | Status | Responsible | Category | Module com | Category com
T2026.03 | CLD | Divya | Open/New | SPC Application team | Application Dump Issue | PDE | Application Dump Issue
T2026.05 | ITSM | Yashaswini | In Progress | Start Team | Oberon5 UI Issue | TDE | Script maintenance Issue
T2026.07 | PRE | Rashmi | Passed | Test Automation team | Script maintenance Issue | TEX | Step Issue
T2026.09 | ROT | Sushma |  | Qmate Team | Start Issue | SPR | Application Data Issue
T2026.11 | SWC | Gunjan |  |  | Step Issue | DIS | UI Change Issue
T2026.13 | CNP | Kamalaveni |  |  | Application Data Issue | DDE | Application Bug
T2026.15 | ISS | Kavitha |  |  | UI Enhancement by Dev | DDV | Qmate Issue
T2026.17 | IES | Sanjay |  |  | Application Bug- Status mismatch | DRE | Decrypt Issue
T2026.19 | IPS | Manjula |  |  | Qmate Issue | CON | UI5 selectors change
T2026.21 | ICSM | Hamsa |  |  | Application Bug- Text mismatch | PPA | Application Bug- Status mismatch
T2026.23 | ICN |  |  |  | Application Bug- pop upText mismatch | Tool issue | Application Bug- Text mismatch
T2026.25 | IAM |  |  |  | Application Bug- selector not found/disabled |  | Application Bug- pop upText mismatch
T2026.27 | PRV |  |  |  | Application Bug- error message not available |  | Application Bug- selector not found/disabled
T2026.29 | CAM |  |  |  | Application Bug- success message not available |  | Application Bug- error message not available
T2026.31 | Cloud Infra |  |  |  | Application Bug- Save fails |  | Application Bug- success message not available
T2026.33 |  |  |  |  | Application Bug- Locking object Error |  | Application Bug- Save fails
T2026.35 |  |  |  |  | Application Bug- User auth error |  | Application Bug- Locking object Error
T2026.37 |  |  |  |  | Application Bug- API response error |  | Application Bug- User auth error
T2026.39 |  |  |  |  | Application Bug- Element not found |  | Application Bug- API response error
T2026.41
T2026.43
T2026.45
T2026.47
T2026.49
T2026.51
T2026.53
T2026.55
T2026.57
T2026.59